## Member 1 - Leader
Member 1 - Leader
Vai trò: Team Leader + Infrastructure + Java Backend
Kỹ năng: Java, Python, Kafka, Kubernetes, System Integration
Tuần | Công việc | Status | Mô tả | Deliverables
TUẦN 1: Infrastructure Foundation
1 | Setup Kafka cluster | PENDING | Confluent Cloud hoặc Local với Docker. Tạo topics: orders_raw, orders_enriched, revenue_metrics. Test producer/consumer | Kafka topics ready; MongoDB collections created; MinIO buckets ready; GitHub repo structure; config/ folder với connection configs
1 | Setup MongoDB Atlas | PENDING | Tạo database olist_analytics. Tạo collections: revenue_metrics, customer_segments, product_performance | Kafka topics ready; MongoDB collections created; MinIO buckets ready; GitHub repo structure; config/ folder với connection configs
1 | Setup MinIO | PENDING | S3-compatible storage. Tạo buckets: bronze, silver, gold. Test upload/download | Kafka topics ready; MongoDB collections created; MinIO buckets ready; GitHub repo structure; config/ folder với connection configs
1 | Setup GitHub repository | PENDING | Tạo folder structure theo README. Setup branch strategy (dev, feature branches) | Kafka topics ready; MongoDB collections created; MinIO buckets ready; GitHub repo structure; config/ folder với connection configs
1 | Document connection strings | PENDING | Document connection strings và credentials | Kafka topics ready; MongoDB collections created; MinIO buckets ready; GitHub repo structure; config/ folder với connection configs
TUẦN 2: Kubernetes & Integration
2 | Setup Minikube | PENDING | Install Minikube. Start cluster. Verify kubectl working | Minikube running; K8s manifests created; Airflow operational; Integration tests passing
2 | Create Kubernetes manifests | PENDING | deployment/k8s/namespace.yaml, debezium-deployment.yaml, configmap.yaml | Minikube running; K8s manifests created; Airflow operational; Integration tests passing
2 | Setup Airflow | PENDING | docker-compose for Airflow. Access Airflow UI. Create first DAG | Minikube running; K8s manifests created; Airflow operational; Integration tests passing
2 | Integration testing | PENDING | Test Kafka → MongoDB connectivity. Test MinIO read/write from Spark | Minikube running; K8s manifests created; Airflow operational; Integration tests passing
2 | Code review setup | PENDING | Setup PR template. Define code review process | Minikube running; K8s manifests created; Airflow operational; Integration tests passing
TUẦN 3: Monitoring & Code Review
3 | Setup monitoring framework | PENDING | Install Prometheus (optional). Configure Spark metrics. Create metrics dashboard template | Monitoring framework setup; Code reviews completed; Integration test framework ready
3 | Code review for all members | PENDING | Review Spark code quality. Check naming conventions. Verify error handling | Monitoring framework setup; Code reviews completed; Integration test framework ready
3 | Create integration test framework | PENDING | tests/integration/ structure. Pytest setup. Sample test cases | Monitoring framework setup; Code reviews completed; Integration test framework ready
3 | Weekly progress meeting | PENDING | Review deliverables. Identify blockers. Adjust timeline if needed | Monitoring framework setup; Code reviews completed; Integration test framework ready
TUẦN 4: Performance Monitoring
4 | Setup Spark UI monitoring | PENDING | Access Spark UI (port 4040). Analyze job stages. Identify shuffle operations | Spark UI monitoring documented; Optimal Spark configs identified; Cost analysis report
4 | Resource allocation tuning | PENDING | Tune Spark configs. Document optimal settings | Spark UI monitoring documented; Optimal Spark configs identified; Cost analysis report
4 | Cost analysis | PENDING | Estimate cloud costs. Resource usage report. Optimization recommendations | Spark UI monitoring documented; Optimal Spark configs identified; Cost analysis report
4 | Code review optimization work | PENDING | Review Member 3's optimization work | Spark UI monitoring documented; Optimal Spark configs identified; Cost analysis report
TUẦN 5: Airflow DAGs for Streaming
5 | Create Airflow DAG for stream monitoring | PENDING | Check Kafka consumer lag. Check Spark streaming job status. Alert if lag > threshold | Airflow monitoring DAG; Integration tests passing; Documentation updated
5 | Integration testing | PENDING | End-to-end test: Postgres → Kafka → Spark → MongoDB. Data consistency checks. Latency measurements | Airflow monitoring DAG; Integration tests passing; Documentation updated
5 | Documentation | PENDING | Update architecture diagram. Document data flows. API documentation | Airflow monitoring DAG; Integration tests passing; Documentation updated
TUẦN 6: Kubernetes Deployment
6 | Deploy Spark Streaming on K8s | PENDING | Create Spark on K8s YAML. Deploy streaming job. Test auto-restart on failure | Streaming job on Kubernetes; CI/CD pipeline (basic); Load testing results; Deployment documentation
6 | Setup CI/CD pipeline | PENDING | GitHub Actions for build. Automated tests. Docker image build | Streaming job on Kubernetes; CI/CD pipeline (basic); Load testing results; Deployment documentation
6 | Load testing streaming pipeline | PENDING | Generate high event rate. Monitor Kafka lag. Measure end-to-end latency | Streaming job on Kubernetes; CI/CD pipeline (basic); Load testing results; Deployment documentation
6 | Document deployment process | PENDING | Deployment guide. Troubleshooting tips | Streaming job on Kubernetes; CI/CD pipeline (basic); Load testing results; Deployment documentation
TUẦN 7: Service Integration
7 | Implement service discovery | PENDING | Kubernetes Services. Service mesh (optional). DNS-based discovery | Service discovery working; Load balancing configured; E2E integration tests passing; Integration test suite created
7 | Implement load balancing | PENDING | Kafka partition assignment. Consumer group management. Load balancer config | Service discovery working; Load balancing configured; E2E integration tests passing; Integration test suite created
7 | End-to-end integration testing | PENDING | Test full pipeline. Data consistency validation. Performance testing. Failure recovery testing | Service discovery working; Load balancing configured; E2E integration tests passing; Integration test suite created
7 | Create integration test suite | PENDING | Automated E2E tests. Test data generator. Validation scripts | Service discovery working; Load balancing configured; E2E integration tests passing; Integration test suite created
TUẦN 8: MLflow Setup & Code Review
8 | Setup MLflow | PENDING | Install MLflow. Configure tracking server. Model registry | MLflow setup (optional); ML code review completed; Model deployment guide; ML integration tests
8 | Code review for ML code | PENDING | Review model training code. Verify evaluation metrics. Check for overfitting | MLflow setup (optional); ML code review completed; Model deployment guide; ML integration tests
8 | Create model deployment guide | PENDING | How to load models. How to make predictions. Model versioning strategy | MLflow setup (optional); ML code review completed; Model deployment guide; ML integration tests
8 | Integration testing with ML models | PENDING | Test batch prediction. Test real-time prediction | MLflow setup (optional); ML code review completed; Model deployment guide; ML integration tests
TUẦN 9: Integration & Performance Testing
9 | End-to-end integration testing | PENDING | Data flow validation. Data consistency checks. Latency measurements. Throughput testing | E2E integration tests passing; Performance tuning completed; Load testing report; Deployment runbook
9 | Performance tuning | PENDING | Identify bottlenecks. Optimize slow queries. Tune Spark configurations. Optimize Kafka settings | E2E integration tests passing; Performance tuning completed; Load testing report; Deployment runbook
9 | Load testing | PENDING | Generate high data volume. Stress test all components. Measure breaking points. Document results | E2E integration tests passing; Performance tuning completed; Load testing report; Deployment runbook
9 | Create deployment runbook | PENDING | Step-by-step deployment guide. Configuration checklist. Troubleshooting guide. Rollback procedures | E2E integration tests passing; Performance tuning completed; Load testing report; Deployment runbook
TUẦN 10: Final Report & Presentation
10 | Write final report (30-40 pages) | PENDING | Introduction, Architecture, Tech Stack, Implementation, Spark Features, Testing, Monitoring, Challenges, Future Work | Final report (30-40 pages); Presentation slides (20-25 slides); Demo video (10-15 min); Q&A document
10 | Create presentation slides (20-25) | PENDING | Title, Problem, Architecture, Spark Features DEMO, Streaming, ML, Results, Challenges, Demo, Future, Q&A | Final report (30-40 pages); Presentation slides (20-25 slides); Demo video (10-15 min); Q&A document
10 | Record demo video (10-15 min) | PENDING | Introduction. Architecture walkthrough. Live demo. Grafana dashboards. Code walkthrough. Q&A prep | Final report (30-40 pages); Presentation slides (20-25 slides); Demo video (10-15 min); Q&A document
10 | Prepare Q&A document | PENDING | Anticipate questions. Prepare answers. Technical deep dives ready | Final report (30-40 pages); Presentation slides (20-25 slides); Demo video (10-15 min); Q&A document

## Member 2 - Java Dev
Member 2 - Java Dev
Vai trò: Java Backend Engineer + CDC Specialist
Kỹ năng: Java, Spring Boot, Kafka, PostgreSQL, Debezium
Tuần | Công việc | Status | Mô tả | Deliverables
TUẦN 1: PostgreSQL & Development Environment
1 | Setup PostgreSQL database | PENDING | Install PostgreSQL 15+. Enable WAL for CDC. Create database olist_db | PostgreSQL installed và configured for CDC; Java Spring Boot project initialized; Development environment ready
1 | Create Java Spring Boot project | PENDING | Initialize Maven/Gradle project. Add dependencies: Spring Boot, Kafka, MongoDB, PostgreSQL. Setup application.properties template | PostgreSQL installed và configured for CDC; Java Spring Boot project initialized; Development environment ready
1 | Study Debezium CDC concepts | PENDING | Read Debezium documentation. Prepare CDC configuration template | PostgreSQL installed và configured for CDC; Java Spring Boot project initialized; Development environment ready
1 | Install development tools | PENDING | Java 17, Maven, IntelliJ IDEA. Kafka command-line tools | PostgreSQL installed và configured for CDC; Java Spring Boot project initialized; Development environment ready
TUẦN 2: Data Loading & CDC Setup
2 | Load Olist data vào PostgreSQL | PENDING | Create tables schema (9 tables). Write data loading scripts. Load augmented dataset (2-3GB). Verify data integrity | PostgreSQL tables created and loaded with data; Debezium CDC capturing changes; Java Kafka producer working
2 | Setup Debezium CDC | PENDING | Configure Debezium connector for PostgreSQL. Deploy Debezium trên Kubernetes. Test CDC capturing changes | PostgreSQL tables created and loaded with data; Debezium CDC capturing changes; Java Kafka producer working
2 | Create Java Kafka Producer (test) | PENDING | Simple producer để test Kafka. Send test messages. Verify messages in Kafka topic | PostgreSQL tables created and loaded with data; Debezium CDC capturing changes; Java Kafka producer working
TUẦN 3: Assist Batch + Start Java Consumer
3 | Assist Member 3 with Spark SQL | PENDING | Review join strategies. Help debug performance issues | Java Kafka Consumer reading messages; MongoDB Java driver working; Error handling framework implemented
3 | Start Java Kafka Consumer project | PENDING | services/java-consumer/ project. Spring Boot + Kafka consumer. Deserialize messages. Log messages | Java Kafka Consumer reading messages; MongoDB Java driver working; Error handling framework implemented
3 | Study MongoDB Java driver | PENDING | Add MongoDB dependency. Create connection class. Test CRUD operations | Java Kafka Consumer reading messages; MongoDB Java driver working; Error handling framework implemented
3 | Create error handling framework | PENDING | Dead letter queue (DLQ) pattern. Retry logic. Circuit breaker (Resilience4j) | Java Kafka Consumer reading messages; MongoDB Java driver working; Error handling framework implemented
TUẦN 4: MongoDB Writer Service
4 | Create MongoDB writer microservice | PENDING | services/java-mongodb-writer/ Spring Boot. REST API. Kafka consumer. Write to MongoDB | Java MongoDB writer service working; Kafka → Java → MongoDB pipeline operational; Docker images created
4 | Implement batch write optimization | PENDING | Bulk insert API. Connection pooling. Retry mechanism | Java MongoDB writer service working; Kafka → Java → MongoDB pipeline operational; Docker images created
4 | Add health check endpoint | PENDING | /health endpoint. Check Kafka connection. Check MongoDB connection | Java MongoDB writer service working; Kafka → Java → MongoDB pipeline operational; Docker images created
4 | Dockerize Java services | PENDING | Create Dockerfile. docker-compose for local testing. Push to Docker Hub (optional) | Java MongoDB writer service working; Kafka → Java → MongoDB pipeline operational; Docker images created
TUẦN 5: Kafka Producer Enhancement
5 | Enhance Java Kafka Producer | PENDING | Read from PostgreSQL periodically. Produce to Kafka topics. Transactional writes (exactly-once) | Kafka producer producing events; Metrics exported; Load testing results
5 | Implement CDC listener | PENDING | PostgreSQL logical replication. Capture INSERT/UPDATE/DELETE. Produce events to Kafka | Kafka producer producing events; Metrics exported; Load testing results
5 | Add metrics | PENDING | Prometheus metrics export. Messages produced per second. Error count | Kafka producer producing events; Metrics exported; Load testing results
5 | Load testing | PENDING | Generate high volume of events. Measure throughput. Identify bottlenecks | Kafka producer producing events; Metrics exported; Load testing results
TUẦN 6: Circuit Breaker & Resilience
6 | Implement Circuit Breaker pattern | PENDING | Use Resilience4j. Circuit breaker for MongoDB writes. Circuit breaker for Kafka producer | Circuit breaker implemented; Retry logic working; Comprehensive logging added; Integration tests passing
6 | Implement retry logic | PENDING | Exponential backoff. Max retry attempts. Dead letter queue (DLQ) | Circuit breaker implemented; Retry logic working; Comprehensive logging added; Integration tests passing
6 | Add comprehensive logging | PENDING | Structured logging (JSON). Log levels configuration. Correlation IDs for tracing | Circuit breaker implemented; Retry logic working; Comprehensive logging added; Integration tests passing
6 | Integration testing | PENDING | Test failure scenarios. Verify circuit breaker opens. Verify retry logic works | Circuit breaker implemented; Retry logic working; Comprehensive logging added; Integration tests passing
TUẦN 7: Java Consumer & Producer Complete
7 | Complete Java Kafka Consumer | PENDING | Consume from multiple topics. Parallel processing. Offset management. Consumer group config | Java Kafka consumer operational; Java MongoDB writer operational; Data enrichment service working; Monitoring endpoints available; Performance tuning completed
7 | Complete Java MongoDB Writer | PENDING | Batch writes. Bulk upsert. Connection pooling. Write performance optimization | Java Kafka consumer operational; Java MongoDB writer operational; Data enrichment service working; Monitoring endpoints available; Performance tuning completed
7 | Implement data enrichment service | PENDING | Read from Kafka. Enrich with reference data. Write enriched data to Kafka. Add product details to orders | Java Kafka consumer operational; Java MongoDB writer operational; Data enrichment service working; Monitoring endpoints available; Performance tuning completed
7 | Add monitoring endpoints | PENDING | /metrics for Prometheus. /health endpoint. /info endpoint. Consumer lag metrics | Java Kafka consumer operational; Java MongoDB writer operational; Data enrichment service working; Monitoring endpoints available; Performance tuning completed
7 | Performance tuning | PENDING | JVM tuning. Thread pool sizing. Memory management. Benchmark results | Java Kafka consumer operational; Java MongoDB writer operational; Data enrichment service working; Monitoring endpoints available; Performance tuning completed
TUẦN 8: ML Model Serving (Optional)
8 | Create model serving API | PENDING | REST API to serve predictions. Load ML model (PMML/ONNX). Prediction endpoint | ML serving API (optional); ML infrastructure support provided; Java documentation completed; Performance testing done
8 | Assist Member 5 with ML | PENDING | Help with data pipeline for ML. Review ML code | ML serving API (optional); ML infrastructure support provided; Java documentation completed; Performance testing done
8 | Finalize Java services documentation | PENDING | API documentation. Deployment guide. Configuration guide | ML serving API (optional); ML infrastructure support provided; Java documentation completed; Performance testing done
8 | Performance testing Java services | PENDING | Load testing. Stress testing. Benchmark results | ML serving API (optional); ML infrastructure support provided; Java documentation completed; Performance testing done
TUẦN 9: Monitoring & Logging
9 | Centralized logging setup | PENDING | Configure structured logging. Log aggregation. Log correlation IDs | Centralized logging working; Metrics collection operational; Health checks configured; Testing completed
9 | Metrics collection | PENDING | Expose Prometheus metrics from Java. JVM metrics. Application metrics | Centralized logging working; Metrics collection operational; Health checks configured; Testing completed
9 | Health checks | PENDING | Kubernetes liveness probes. Readiness probes. Dependency health checks | Centralized logging working; Metrics collection operational; Health checks configured; Testing completed
9 | Testing | PENDING | Integration tests for Java services. Error scenario testing. Performance regression tests | Centralized logging working; Metrics collection operational; Health checks configured; Testing completed
TUẦN 10: Java Services Documentation
10 | Write Java services documentation | PENDING | Architecture of Java services. API documentation (OpenAPI/Swagger). Configuration guide. Deployment guide | Java documentation completed; API documentation; Deployment guide; Demo scenarios prepared
10 | Code documentation | PENDING | Javadoc for all classes. README for each service. Example usage | Java documentation completed; API documentation; Deployment guide; Demo scenarios prepared
10 | Create deployment guide | PENDING | Docker deployment. Kubernetes deployment. Configuration management | Java documentation completed; API documentation; Deployment guide; Demo scenarios prepared
10 | Prepare demo scenarios | PENDING | Java Kafka consumer demo. MongoDB writer performance demo. Circuit breaker demo | Java documentation completed; API documentation; Deployment guide; Demo scenarios prepared

## Member 3 - Spark Batch
Member 3 - Spark Batch
Vai trò: PySpark Batch Processing Specialist
Kỹ năng: PySpark, Data Transformation, Performance Optimization
Tuần | Công việc | Status | Mô tả | Deliverables
TUẦN 1: Dataset & Spark Setup
1 | Download full Olist dataset | PENDING | Download từ Kaggle. Verify data integrity. Place in data/external/. All 9 CSV files | All 9 CSV files downloaded; PySpark working locally; Data exploration report; Data augmentation script
1 | Setup PySpark environment | PENDING | Install Java 17, Python 3.12, Spark 3.5.8. Configure SPARK_HOME, JAVA_HOME. Test Spark local mode | All 9 CSV files downloaded; PySpark working locally; Data exploration report; Data augmentation script
1 | Data exploration & profiling | PENDING | Load all 9 CSV files. Check schema, nulls, data types. Create data dictionary. Write exploration notebook | All 9 CSV files downloaded; PySpark working locally; Data exploration report; Data augmentation script
1 | Create data augmentation script | PENDING | Script to duplicate data 10x. Add timestamp variations. Target: 2-3GB dataset | All 9 CSV files downloaded; PySpark working locally; Data exploration report; Data augmentation script
TUẦN 2: Bronze Layer Ingestion
2 | Create data_ingestion.py | PENDING | Read 9 CSV files. Validate schemas. Handle data quality issues. Write to Bronze layer (MinIO) as Parquet. Partition by date | Bronze layer populated with Parquet files; Data quality report; Airflow DAG working; Incremental loading tested
2 | Create data quality framework | PENDING | Check nulls, duplicates. Schema validation. Data profiling stats. Generate quality report | Bronze layer populated with Parquet files; Data quality report; Airflow DAG working; Incremental loading tested
2 | Create Airflow DAG | PENDING | DAG: batch_ingestion_dag.py. Schedule: daily. Error handling | Bronze layer populated with Parquet files; Data quality report; Airflow DAG working; Incremental loading tested
2 | Test incremental loading | PENDING | Support append mode. Deduplication logic | Bronze layer populated with Parquet files; Data quality report; Airflow DAG working; Incremental loading tested
TUẦN 3: Joins & UDFs ⭐
3 | Implement Broadcast Join | PENDING | orders ⋈ product_categories (small table). Use broadcast() function | Broadcast join implemented and working; Sort-merge join implemented; 3+ UDFs created and tested; Silver layer data written; Execution plan analysis document
3 | Implement Sort-Merge Join | PENDING | orders ⋈ order_items ⋈ products (large tables). Repartition and sortWithinPartitions | Broadcast join implemented and working; Sort-merge join implemented; 3+ UDFs created and tested; Silver layer data written; Execution plan analysis document
3 | Implement Multiple Join | PENDING | orders ⋈ items ⋈ products ⋈ sellers ⋈ customers. Analyze execution plans | Broadcast join implemented and working; Sort-merge join implemented; 3+ UDFs created and tested; Silver layer data written; Execution plan analysis document
3 | Create 3+ custom UDFs | PENDING | Calculate discount percentage. Classify delivery status. Customer segment classifier | Broadcast join implemented and working; Sort-merge join implemented; 3+ UDFs created and tested; Silver layer data written; Execution plan analysis document
3 | Write Silver layer | PENDING | Partition by year and month. Parquet with Snappy compression. Schema evolution handling | Broadcast join implemented and working; Sort-merge join implemented; 3+ UDFs created and tested; Silver layer data written; Execution plan analysis document
TUẦN 4: Advanced Transformations ⭐
4 | Implement Window Functions | PENDING | Ranking: Top 10 products per category. Lead/Lag: Month-over-month growth. Running Totals: Cumulative spend | Window functions implemented (3+ examples); Pivot/Unpivot working; Partitioned data in MinIO; Bucketed tables created; Caching strategies applied; Performance improvement report (before/after metrics)
4 | Implement Pivot/Unpivot | PENDING | Pivot: Payment methods by state. Unpivot: using stack function | Window functions implemented (3+ examples); Pivot/Unpivot working; Partitioned data in MinIO; Bucketed tables created; Caching strategies applied; Performance improvement report (before/after metrics)
4 | Implement Partitioning & Bucketing | PENDING | Partition by year, month. Bucket frequently joined tables | Window functions implemented (3+ examples); Pivot/Unpivot working; Partitioned data in MinIO; Bucketed tables created; Caching strategies applied; Performance improvement report (before/after metrics)
4 | Implement Caching Strategies | PENDING | Cache frequently accessed DataFrames. Persist with storage level. Unpersist when done | Window functions implemented (3+ examples); Pivot/Unpivot working; Partitioned data in MinIO; Bucketed tables created; Caching strategies applied; Performance improvement report (before/after metrics)
4 | Performance benchmarking | PENDING | Benchmark before optimization. Apply optimizations. Benchmark after. Document improvements | Window functions implemented (3+ examples); Pivot/Unpivot working; Partitioned data in MinIO; Bucketed tables created; Caching strategies applied; Performance improvement report (before/after metrics)
TUẦN 5: Support Streaming
5 | Assist Member 4 with Streaming | PENDING | Debug streaming queries. Help with transformations | Streaming support provided; Batch jobs optimized; Utility library created
5 | Optimize batch jobs | PENDING | Apply learnings from week 4. Refactor code for reusability. Add unit tests | Streaming support provided; Batch jobs optimized; Utility library created
5 | Create reusable Spark utilities | PENDING | utils/spark_utils.py. Common transformations. UDF library. Configuration loader | Streaming support provided; Batch jobs optimized; Utility library created
TUẦN 6: Testing & Documentation
6 | Write unit tests | PENDING | Test UDFs. Test transformations. Test aggregations. Use pytest + pyspark test utils | Unit tests (>80% coverage); Integration tests passing; Code refactored; Documentation completed
6 | Write integration tests | PENDING | End-to-end batch pipeline test. Data quality tests. Performance regression tests | Unit tests (>80% coverage); Integration tests passing; Code refactored; Documentation completed
6 | Code refactoring | PENDING | Extract common functions. Improve code readability. Add docstrings | Unit tests (>80% coverage); Integration tests passing; Code refactored; Documentation completed
6 | Documentation | PENDING | Batch processing guide. Performance tuning guide. API documentation | Unit tests (>80% coverage); Integration tests passing; Code refactored; Documentation completed
TUẦN 7: Batch-Stream Integration
7 | Create unified data model | PENDING | Reconcile batch and streaming schemas. Merge batch and streaming results in MongoDB. Deduplication logic | Unified data model; Lambda serving layer; Reconciliation job working; Performance comparison report
7 | Implement Lambda serving layer | PENDING | Batch view + Real-time view merge. Query API (Flask/FastAPI). Serve queries from MongoDB | Unified data model; Lambda serving layer; Reconciliation job working; Performance comparison report
7 | Create data reconciliation job | PENDING | Compare batch and streaming results. Identify discrepancies. Generate reconciliation report | Unified data model; Lambda serving layer; Reconciliation job working; Performance comparison report
7 | Performance comparison | PENDING | Batch vs streaming latency. Resource utilization. Cost analysis | Unified data model; Lambda serving layer; Reconciliation job working; Performance comparison report
TUẦN 8: Support ML Data Prep
8 | Assist Member 5 with data prep | PENDING | Feature engineering pipeline. Data sampling for training. Data validation | ML data prep support completed; Batch jobs optimized for ML; Data export utilities created; Code cleaned up
8 | Optimize batch jobs for ML | PENDING | Efficient feature extraction. Caching intermediate results | ML data prep support completed; Batch jobs optimized for ML; Data export utilities created; Code cleaned up
8 | Create data export utilities | PENDING | Export data for ML (CSV, Parquet). Sampling utilities. Data versioning | ML data prep support completed; Batch jobs optimized for ML; Data export utilities created; Code cleaned up
8 | Code cleanup and refactoring | PENDING | Remove dead code. Improve modularity. Add more unit tests | ML data prep support completed; Batch jobs optimized for ML; Data export utilities created; Code cleaned up
TUẦN 9: Testing & Documentation
9 | Comprehensive testing | PENDING | Unit tests for all functions. Integration tests for pipelines. Data quality tests. Performance regression tests | Test coverage >80%; All tests passing; Documentation completed; Demo scenarios prepared
9 | Test coverage report | PENDING | Measure code coverage (>80% target). Identify untested code. Add missing tests | Test coverage >80%; All tests passing; Documentation completed; Demo scenarios prepared
9 | Documentation | PENDING | Batch processing user guide. Code documentation (docstrings). Performance tuning guide. Troubleshooting guide | Test coverage >80%; All tests passing; Documentation completed; Demo scenarios prepared
9 | Create demo scenarios | PENDING | Demo 1: Batch processing pipeline. Demo 2: Performance optimization. Demo 3: Data quality checks | Test coverage >80%; All tests passing; Documentation completed; Demo scenarios prepared
TUẦN 10: Batch Processing Documentation
10 | Write batch documentation | PENDING | Architecture of batch pipeline. Data flow explanation. Performance optimization guide. Troubleshooting guide | Batch documentation completed; Code documentation; Demo notebook; Report contribution
10 | Create code documentation | PENDING | Docstrings for all functions. README for each module. Example usage | Batch documentation completed; Code documentation; Demo notebook; Report contribution
10 | Create demo notebook | PENDING | Jupyter notebook demonstrating: Broadcast join, Window functions, Pivot operations, Performance optimization | Batch documentation completed; Code documentation; Demo notebook; Report contribution
10 | Contribute to final report | PENDING | Batch processing section. Performance metrics section | Batch documentation completed; Code documentation; Demo notebook; Report contribution

## Member 4 - Spark Streaming
Member 4 - Spark Streaming
Vai trò: PySpark Streaming Specialist
Kỹ năng: Spark Structured Streaming, Real-time Processing, Watermarking
Tuần | Công việc | Status | Mô tả | Deliverables
TUẦN 1: Streaming Study & Prep
1 | Study Spark Structured Streaming | PENDING | Read official documentation. Complete streaming tutorials. Understand window operations | Streaming concepts documented; Test data generator script ready; Development environment ready
1 | Study Kafka integration with Spark | PENDING | Kafka-Spark connector. Schema management. Offset management | Streaming concepts documented; Test data generator script ready; Development environment ready
1 | Prepare streaming test data generator | PENDING | Python script to produce fake orders to Kafka. Configurable rate (orders/second) | Streaming concepts documented; Test data generator script ready; Development environment ready
1 | Install development tools | PENDING | Python 3.12, PySpark 3.5.8. Kafka Python client | Streaming concepts documented; Test data generator script ready; Development environment ready
TUẦN 2: Kafka Consumer Setup
2 | Create kafka_consumer.py | PENDING | Read from Kafka topic orders_raw. Parse JSON messages. Schema definition. Write to console (testing) | Kafka consumer reading messages; Checkpoint mechanism working; Streaming architecture document
2 | Test streaming pipeline basics | PENDING | Use test data generator. Verify Spark can read from Kafka. Check offset management | Kafka consumer reading messages; Checkpoint mechanism working; Streaming architecture document
2 | Create checkpoint directory | PENDING | Setup checkpoint location in MinIO. Test recovery after failure | Kafka consumer reading messages; Checkpoint mechanism working; Streaming architecture document
2 | Document streaming architecture | PENDING | Data flow diagram. Kafka topics mapping | Kafka consumer reading messages; Checkpoint mechanism working; Streaming architecture document
TUẦN 3: Assist Batch + Streaming Prep
3 | Assist Member 3 with batch | PENDING | Help debug join issues. Performance testing | Batch processing support completed; Streaming data generator ready; Streaming connection tested
3 | Prepare streaming transformations | PENDING | Design window aggregations. Plan watermarking strategy. Schema for streaming data | Batch processing support completed; Streaming data generator ready; Streaming connection tested
3 | Create streaming data generator | PENDING | Produce realistic order events to Kafka. Configurable event rate. Late arrival simulation (10% delayed) | Batch processing support completed; Streaming data generator ready; Streaming connection tested
3 | Test Kafka-Spark streaming | PENDING | Read from Kafka in streaming mode. Write to console. Verify latency | Batch processing support completed; Streaming data generator ready; Streaming connection tested
TUẦN 4: Streaming Architecture
4 | Design streaming architecture doc | PENDING | Data flow diagram. Topic naming conventions. Schema registry strategy | Streaming architecture document; Test scenarios prepared; Monitoring dashboard template; Stateful streaming concepts documented
4 | Prepare watermarking test scenarios | PENDING | Late data simulation. Different watermark thresholds. Impact analysis | Streaming architecture document; Test scenarios prepared; Monitoring dashboard template; Stateful streaming concepts documented
4 | Create monitoring dashboard template | PENDING | Kafka lag metrics. Processing rate. Error rate | Streaming architecture document; Test scenarios prepared; Monitoring dashboard template; Stateful streaming concepts documented
4 | Study stateful streaming | PENDING | mapGroupsWithState API. flatMapGroupsWithState API. State timeout mechanisms | Streaming architecture document; Test scenarios prepared; Monitoring dashboard template; Stateful streaming concepts documented
TUẦN 5: Basic Streaming ⭐
5 | Read from Kafka and parse | PENDING | Create streaming_aggregations.py. Read from orders_raw. Parse JSON messages | Kafka → Spark Streaming working; Tumbling window implemented; Sliding window implemented; Streaming → MongoDB working; Streaming → MinIO working; Output modes tested
5 | Implement Tumbling Window | PENDING | Revenue per 5 minutes. With watermark (10 minutes) | Kafka → Spark Streaming working; Tumbling window implemented; Sliding window implemented; Streaming → MongoDB working; Streaming → MinIO working; Output modes tested
5 | Implement Sliding Window | PENDING | Moving 1-hour revenue (slide 10 minutes). With watermark | Kafka → Spark Streaming working; Tumbling window implemented; Sliding window implemented; Streaming → MongoDB working; Streaming → MinIO working; Output modes tested
5 | Write to MongoDB (streaming) | PENDING | Use foreachBatch. Output mode: update | Kafka → Spark Streaming working; Tumbling window implemented; Sliding window implemented; Streaming → MongoDB working; Streaming → MinIO working; Output modes tested
5 | Write to MinIO | PENDING | Checkpoint + data. Trigger: processingTime 1 minute | Kafka → Spark Streaming working; Tumbling window implemented; Sliding window implemented; Streaming → MongoDB working; Streaming → MinIO working; Output modes tested
5 | Test output modes | PENDING | Append, Update, Complete modes | Kafka → Spark Streaming working; Tumbling window implemented; Sliding window implemented; Streaming → MongoDB working; Streaming → MinIO working; Output modes tested
TUẦN 6: Advanced Streaming ⭐
6 | Implement Watermarking | PENDING | Allow 10 minutes of late data. Test with late data injection. Measure data loss. Document strategy | Watermarking implemented and tested; Session windows working; Stateful streaming implemented; Exactly-once semantics verified; Checkpoint recovery tested
6 | Implement Session Windows | PENDING | Session window: gap of 30 minutes. Customer session analysis | Watermarking implemented and tested; Session windows working; Stateful streaming implemented; Exactly-once semantics verified; Checkpoint recovery tested
6 | Implement Stateful Streaming | PENDING | mapGroupsWithState for session tracking. Update user session state | Watermarking implemented and tested; Session windows working; Stateful streaming implemented; Exactly-once semantics verified; Checkpoint recovery tested
6 | Implement Exactly-Once | PENDING | Kafka transactional writes. Idempotent writes to MongoDB. Test duplicate detection | Watermarking implemented and tested; Session windows working; Stateful streaming implemented; Exactly-once semantics verified; Checkpoint recovery tested
6 | Checkpoint management | PENDING | Optimize checkpoint interval. Test recovery. Monitor checkpoint size | Watermarking implemented and tested; Session windows working; Stateful streaming implemented; Exactly-once semantics verified; Checkpoint recovery tested
TUẦN 7: Streaming Optimization
7 | Optimize streaming performance | PENDING | Tune Kafka consumer settings. Optimize trigger interval. Minimize shuffle operations. Coalesce/Repartition | Streaming performance optimized; Real-time analytics implemented; Monitoring metrics added; Failure recovery tested and documented
7 | Implement streaming analytics | PENDING | Real-time fraud detection (simple rules). Anomaly detection (statistical). Trending products detection | Streaming performance optimized; Real-time analytics implemented; Monitoring metrics added; Failure recovery tested and documented
7 | Add stream monitoring | PENDING | Processing rate metrics. Batch processing time. Watermark delay metrics. State size monitoring | Streaming performance optimized; Real-time analytics implemented; Monitoring metrics added; Failure recovery tested and documented
7 | Failure recovery testing | PENDING | Kill streaming job. Verify checkpoint recovery. Measure recovery time. Document recovery procedure | Streaming performance optimized; Real-time analytics implemented; Monitoring metrics added; Failure recovery tested and documented
TUẦN 8: Real-time Feature Engineering
8 | Real-time feature computation | PENDING | Streaming aggregations as features. Rolling window features. Stateful features | Real-time feature engineering; Features in feature store; Feature serving API; ML support provided
8 | Write features to feature store | PENDING | Real-time feature updates to MongoDB. Feature versioning | Real-time feature engineering; Features in feature store; Feature serving API; ML support provided
8 | Create feature serving API | PENDING | FastAPI to query features. Low-latency retrieval. Caching layer | Real-time feature engineering; Features in feature store; Feature serving API; ML support provided
8 | Assist Member 5 with ML | PENDING | Help with streaming ML inference. Review ML code | Real-time feature engineering; Features in feature store; Feature serving API; ML support provided
TUẦN 9: Streaming Testing
9 | Streaming integration tests | PENDING | Test window aggregations. Test watermarking with late data. Test stateful processing. Test exactly-once | Streaming tests passing; Failure recovery verified; Performance testing completed; Documentation done
9 | Failure recovery testing | PENDING | Test checkpoint recovery. Test after Kafka restart. Test after Spark restart. Measure recovery time | Streaming tests passing; Failure recovery verified; Performance testing completed; Documentation done
9 | Performance testing | PENDING | Measure processing latency. Measure throughput. Test with different data rates. Document results | Streaming tests passing; Failure recovery verified; Performance testing completed; Documentation done
9 | Documentation | PENDING | Streaming user guide. Troubleshooting guide. Demo scenarios | Streaming tests passing; Failure recovery verified; Performance testing completed; Documentation done
TUẦN 10: Streaming Documentation
10 | Write streaming documentation | PENDING | Architecture of streaming pipeline. Watermarking strategy. Stateful processing guide. Troubleshooting guide | Streaming documentation completed; Code documentation; Demo notebook; Report contribution
10 | Create code documentation | PENDING | Docstrings for all functions. README for streaming module. Example usage | Streaming documentation completed; Code documentation; Demo notebook; Report contribution
10 | Create demo notebook | PENDING | Jupyter notebook: Window aggregations, Watermarking, Stateful processing, Exactly-once semantics | Streaming documentation completed; Code documentation; Demo notebook; Report contribution
10 | Contribute to final report | PENDING | Streaming processing section. Real-time metrics section | Streaming documentation completed; Code documentation; Demo notebook; Report contribution

## Member 5 - Data Scientist
Member 5 - Data Scientist
Vai trò: ML Engineer + Data Analyst + Visualization Engineer
Kỹ năng: MLlib, GraphFrames, Grafana, MongoDB
Tuần | Công việc | Status | Mô tả | Deliverables
TUẦN 1: ML Study & MongoDB Setup
1 | Study Spark MLlib | PENDING | ALS for recommendation. Random Forest for classification. Regression models | ML study notes; MongoDB connection working from Python; MongoDB schema design document; Grafana installed and connected
1 | Study GraphFrames | PENDING | PageRank algorithm. Connected Components. Graph construction | ML study notes; MongoDB connection working from Python; MongoDB schema design document; Grafana installed and connected
1 | Setup MongoDB connection from Python | PENDING | Install pymongo. Test CRUD operations. Create MongoDB schema design document | ML study notes; MongoDB connection working from Python; MongoDB schema design document; Grafana installed and connected
1 | Install Grafana locally | PENDING | Install Grafana. Connect to MongoDB. Create test dashboard | ML study notes; MongoDB connection working from Python; MongoDB schema design document; Grafana installed and connected
TUẦN 2: MongoDB Integration
2 | Create mongo_connector.py | PENDING | Connection manager class. CRUD operations wrappers. Bulk insert optimizations. Upsert logic | MongoDB connector working; Indexes created; Data quality checker ready; Performance benchmark report
2 | Create MongoDB indexes | PENDING | Indexes on collections. Compound indexes. TTL indexes for hot/cold data | MongoDB connector working; Indexes created; Data quality checker ready; Performance benchmark report
2 | Write data quality checker | PENDING | scripts/data_quality.py. Null checks. Duplicate detection. Outlier detection. Generate HTML report | MongoDB connector working; Indexes created; Data quality checker ready; Performance benchmark report
2 | Test MongoDB write performance | PENDING | Benchmark bulk inserts. Query performance testing. Document results | MongoDB connector working; Indexes created; Data quality checker ready; Performance benchmark report
TUẦN 3: Gold Layer Aggregations
3 | Create silver_to_gold.py | PENDING | Revenue aggregations by category, year_month. Sum, count, avg, countDistinct | Gold layer aggregations created; Data written to MongoDB; Data quality dashboard in Grafana
3 | Implement RFM Segmentation | PENDING | Recency: days since last purchase. Frequency: number of orders. Monetary: total spend | Gold layer aggregations created; Data written to MongoDB; Data quality dashboard in Grafana
3 | Product Performance Metrics | PENDING | Top products by revenue. Products by review score. Conversion rate by product | Gold layer aggregations created; Data written to MongoDB; Data quality dashboard in Grafana
3 | Write Gold data to MongoDB | PENDING | Use mongo-spark connector. Upsert mode. Batch write optimization | Gold layer aggregations created; Data written to MongoDB; Data quality dashboard in Grafana
3 | Create data quality dashboard | PENDING | Grafana dashboard. Null percentages. Record counts. Data freshness | Gold layer aggregations created; Data written to MongoDB; Data quality dashboard in Grafana
TUẦN 4: Feature Engineering for ML
4 | Prepare ML datasets | PENDING | Recommendation dataset (user-item matrix). Churn prediction dataset (RFM features). Revenue forecasting dataset (time series features) | ML datasets prepared; Feature engineering pipeline; EDA notebook; Features stored in MongoDB
4 | Feature engineering pipeline | PENDING | services/ml/feature_engineering.py. Scalers and encoders. Handle missing values. Train/test split | ML datasets prepared; Feature engineering pipeline; EDA notebook; Features stored in MongoDB
4 | Exploratory Data Analysis | PENDING | Correlation analysis. Distribution plots. Feature importance (preliminary). Create EDA notebook | ML datasets prepared; Feature engineering pipeline; EDA notebook; Features stored in MongoDB
4 | Write features to MongoDB | PENDING | Collection: ml_features. Versioning strategy | ML datasets prepared; Feature engineering pipeline; EDA notebook; Features stored in MongoDB
TUẦN 5: MongoDB Query Optimization
5 | Analyze query patterns | PENDING | Slow query log analysis. Identify frequent queries. Measure query latency | Query optimization completed; Indexes created; Aggregation pipelines implemented; First Grafana dashboard (draft)
5 | Create additional indexes | PENDING | Compound indexes for common queries. Text indexes for search. Geospatial indexes (if needed) | Query optimization completed; Indexes created; Aggregation pipelines implemented; First Grafana dashboard (draft)
5 | Implement aggregation pipelines | PENDING | MongoDB aggregation for dashboards. Pre-compute heavy aggregations. Materialized views pattern | Query optimization completed; Indexes created; Aggregation pipelines implemented; First Grafana dashboard (draft)
5 | Start Grafana dashboards | PENDING | Dashboard 1: Business Metrics (draft). Connect MongoDB. Create basic panels | Query optimization completed; Indexes created; Aggregation pipelines implemented; First Grafana dashboard (draft)
TUẦN 6: Grafana Dashboards Development
6 | Create Dashboard 2: Customer Analytics | PENDING | Customer segments pie chart. RFM heatmap. Top customers table. CLV trend | Dashboard 2 completed; Dashboard 3 completed; Alerting rules configured; Dashboards optimized
6 | Create Dashboard 3: Product Performance | PENDING | Top products bar chart. Product revenue trend. Review score distribution. Category breakdown | Dashboard 2 completed; Dashboard 3 completed; Alerting rules configured; Dashboards optimized
6 | Add alerting rules | PENDING | Alert if revenue drops > 20%. Alert if error rate > 5%. Alert if Kafka lag > 1000 | Dashboard 2 completed; Dashboard 3 completed; Alerting rules configured; Dashboards optimized
6 | Dashboard optimization | PENDING | Query optimization. Caching strategies. Auto-refresh configuration | Dashboard 2 completed; Dashboard 3 completed; Alerting rules configured; Dashboards optimized
TUẦN 7: Prepare for ML
7 | Finalize ML datasets | PENDING | Feature selection. Train/validation/test split. Data normalization/scaling | ML datasets finalized; ML pipeline structure ready; Feature store in MongoDB; Dashboard 4: System Monitoring completed
7 | Setup ML pipeline structure | PENDING | services/ml/ folder. Model training scripts. Model evaluation framework | ML datasets finalized; ML pipeline structure ready; Feature store in MongoDB; Dashboard 4: System Monitoring completed
7 | Create feature store in MongoDB | PENDING | Collection: feature_store. Versioning mechanism. Feature metadata | ML datasets finalized; ML pipeline structure ready; Feature store in MongoDB; Dashboard 4: System Monitoring completed
7 | Dashboard 4: System Monitoring | PENDING | Kafka metrics. Spark metrics. MongoDB metrics. JVM metrics. System metrics | ML datasets finalized; ML pipeline structure ready; Feature store in MongoDB; Dashboard 4: System Monitoring completed
TUẦN 8: ML & Advanced Analytics ⭐
8 | Train ALS Recommendation model | PENDING | User-item matrix. Train ALS. Evaluate RMSE. Generate top-N recommendations | 3 ML models trained and evaluated; Model performance report; GraphFrames analysis (PageRank, Components, Triangles); Time series analysis; Models saved to MinIO/MongoDB; Jupyter notebooks
8 | Train Churn Prediction model | PENDING | Feature engineering. Train Random Forest. Evaluate AUC, Precision, Recall. Feature importance | 3 ML models trained and evaluated; Model performance report; GraphFrames analysis (PageRank, Components, Triangles); Time series analysis; Models saved to MinIO/MongoDB; Jupyter notebooks
8 | Train Revenue Forecasting model | PENDING | Time series features. Linear Regression or GBT. Evaluate RMSE, R² | 3 ML models trained and evaluated; Model performance report; GraphFrames analysis (PageRank, Components, Triangles); Time series analysis; Models saved to MinIO/MongoDB; Jupyter notebooks
8 | GraphFrames analysis | PENDING | Construct seller-product-customer graph. PageRank: influential sellers. Connected Components. Triangle Count. Motif finding | 3 ML models trained and evaluated; Model performance report; GraphFrames analysis (PageRank, Components, Triangles); Time series analysis; Models saved to MinIO/MongoDB; Jupyter notebooks
8 | Time series analysis | PENDING | Seasonality decomposition. Trend analysis. Anomaly detection (IQR method) | 3 ML models trained and evaluated; Model performance report; GraphFrames analysis (PageRank, Components, Triangles); Time series analysis; Models saved to MinIO/MongoDB; Jupyter notebooks
TUẦN 9: Finalize Dashboards & Visualization
9 | Finalize all Grafana dashboards | PENDING | Dashboard 1-4 polish. Dashboard 5: ML Model Performance (new) | 5 Grafana dashboards finalized; Interactive features added; Alerts configured; Dashboard user guide; ML monitoring dashboard
9 | Add interactive features | PENDING | Drill-down capabilities. Date range selectors. Variable templates | 5 Grafana dashboards finalized; Interactive features added; Alerts configured; Dashboard user guide; ML monitoring dashboard
9 | Configure alerts | PENDING | Revenue anomaly alerts. System health alerts. Data quality alerts. Email/Slack notifications | 5 Grafana dashboards finalized; Interactive features added; Alerts configured; Dashboard user guide; ML monitoring dashboard
9 | Create dashboard user guide | PENDING | How to navigate. What each metric means. How to interpret alerts | 5 Grafana dashboards finalized; Interactive features added; Alerts configured; Dashboard user guide; ML monitoring dashboard
9 | ML model monitoring dashboard | PENDING | Model performance over time. Prediction accuracy. Feature drift detection | 5 Grafana dashboards finalized; Interactive features added; Alerts configured; Dashboard user guide; ML monitoring dashboard
TUẦN 10: ML & Visualization Documentation
10 | Write ML documentation | PENDING | Model architecture & algorithms. Feature engineering explained. Model evaluation & results. GraphFrames analysis. Time series analysis | ML documentation completed; 5 ML notebooks; Dashboard documentation; Report contribution
10 | Create ML notebooks | PENDING | Notebook 1: ALS Recommendation. Notebook 2: Churn Prediction. Notebook 3: Revenue Forecasting. Notebook 4: Graph Analytics. Notebook 5: Time Series | ML documentation completed; 5 ML notebooks; Dashboard documentation; Report contribution
10 | Write dashboard documentation | PENDING | Dashboard user guide. Metrics explanation. How to create alerts | ML documentation completed; 5 ML notebooks; Dashboard documentation; Report contribution
10 | Contribute to final report | PENDING | ML & Analytics section. Visualization section. Results & insights section | ML documentation completed; 5 ML notebooks; Dashboard documentation; Report contribution